## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : MAGNOLIA FANTASIA PHASE-2
Task Name : TOTAL FLOORING WORK ALL TILES WORK
Page 1 of 1
Total Records: 17 Records 1 to 17
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | TOTAL FLOORING WORK ALL TILES WORK | 0 | Started | Material | (M)Silicon Tube | Nos. | 120 | 236 | 28320 | 120 | 236 | 28320 | 0 | 236 | 0 | 120 | 147.5 | 17700 | 0 | 0 | 0 | 120 | 120 | 28320 | 28320
2 | TOTAL FLOORING WORK ALL TILES WORK | 0 | Started | Material | (M)TILES-300X300 | Box | 8844 | 320 | 2830080 | 8844 | 320 | 2830080 | 0 | 320 | 0 | 2481 | 320 | 793930.4062 | 0 | 0 | 0 | 8844 | 8844 | 2830080 | 2830080
3 | TOTAL FLOORING WORK ALL TILES WORK | 0 | Started | Material | (M)TILES-450X300 | Box | 13000 | 320 | 4160000 | 13000 | 320 | 4160000 | 0 | 320 | 0 | 12951 | 320 | 4144374.3942 | 0 | 0 | 0 | 13000 | 13000 | 4160000 | 4160000
4 | TOTAL FLOORING WORK ALL TILES WORK | 0 | Started | Material | (M)TILES-600X600 | Box | 14160 | 728.5 | 10315560 | 14160 | 728.5 | 10315560 | 0 | 728.5 | 0 | 13139 | 622.48 | 8178829.6666 | 0 | 0 | 0 | 14160 | 14160 | 10315560 | 10315560
5 | TOTAL FLOORING WORK ALL TILES WORK | 0 | Started | Labour | (L)FLOOR TILES LABOUR | SQ.FT | 197986 | 15.34 | 3037105.24 | 197986 | 15.34 | 3037105.24 | 0 | 15.34 | 0 | 197986 | 13 | 2573818 | 197986 | 13 | 2573818 | 197986 | 0 | 3037105.24 | 463287.24
6 | TOTAL FLOORING WORK ALL TILES WORK | 0 | Started | Labour | (L)GRANITE GAS HOLE CUTTING LABOUR | Nos. | 396 | 59 | 23364 | 396 | 59 | 23364 | 0 | 59 | 0 | 396 | 50 | 19800 | 396 | 50 | 19800 | 396 | 0 | 23364 | 3564
7 | TOTAL FLOORING WORK ALL TILES WORK | 0 | Started | Labour | (L)GRANITE SINK CUTTING LABOUR | Nos. | 396 | 354 | 140184 | 396 | 354 | 140184 | 0 | 354 | 0 | 396 | 300 | 118800 | 396 | 300 | 118800 | 396 | 0 | 140184 | 21384
8 | TOTAL FLOORING WORK ALL TILES WORK | 0 | Started | Labour | (L)GROUND FLOOR TILES LABOUR | SQ.FT | 10344.866 | 13 | 134483.26 | 10344.865 | 13 | 134483.25 | 0 | 13 | 0 | 5511 | 13 | 71643 | 5511 | 13 | 71643 | 10344.866 | 4833.866 | 134483.258 | 62840.258
9 | TOTAL FLOORING WORK ALL TILES WORK | 0 | Started | Labour | (L)LABOUR CHARGES FOR AMENITIES TILES SKIRTING | R. Ft. | 764.24 | 11 | 8406.64 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 764.24 | 764.24 | 8406.64 | 8406.64
10 | TOTAL FLOORING WORK ALL TILES WORK | 0 | Started | Labour | (L)LABOUR CHARGES FOR PLASTER BACKING | SQ.FT | 1833.689 | 10 | 18336.89 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1833.689 | 1833.689 | 18336.89 | 18336.89
11 | TOTAL FLOORING WORK ALL TILES WORK | 0 | Started | Labour | (L)LABOUR CHARGES FOR SKIRTING | R. Ft. | 68300 | 11 | 751300 | 68300 | 11 | 751300 | 0 | 11 | 0 | 68300 | 11 | 751300 | 68300 | 11 | 751300 | 68300 | 0 | 751300 | 0
12 | TOTAL FLOORING WORK ALL TILES WORK | 0 | Started | Labour | (L)LABOUR CHARGES FOR SWIMMING POOL TOP GRANITE | R. Ft. | 337.184 | 25 | 8429.6 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337.184 | 337.184 | 8429.6 | 8429.6
13 | TOTAL FLOORING WORK ALL TILES WORK | 0 | Started | Labour | (L)LABOUR CHARGES FOR SWIMMING POOL FLOORING WORK | SQ.FT | 1042.488 | 20 | 20849.76 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1042.488 | 1042.488 | 20849.76 | 20849.76
14 | TOTAL FLOORING WORK ALL TILES WORK | 0 | Started | Labour | (L)LIFTING CHARGES OF FLOOR TILES ETC. | Lumpsum | 1 | 25000 | 25000 | 1 | 25000 | 25000 | 0 | 25000 | 0 | 1 | 143000 | 143000 | 1 | 143000 | 143000 | 1 | 0 | 25000 | -118000
15 | TOTAL FLOORING WORK ALL TILES WORK | 0 | Started | Labour | (L)STAIR TREAD GREEN MARBLE LABOUR | R. Ft. | 80.39 | 480 | 38587.2 | 78.392 | 480 | 37628.16 | 0 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.39 | 80.39 | 38587.2 | 38587.2
16 | TOTAL FLOORING WORK ALL TILES WORK | 0 | Started | Labour | (L)SWIMMING POOL WALL TILES LABOUR | SQ.FT | 791.201 | 20 | 15824.02 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 791.201 | 791.201 | 15824.02 | 15824.02
17 | TOTAL FLOORING WORK ALL TILES WORK | 0 | Started | Labour | (L)WALL TILES LABOUR | SQ.FT | 101446 | 17.12 | 1736755.52 | 101446 | 17.12 | 1736755.52 | 0 | 17.12 | 0 | 101446 | 15 | 1521690 | 101446 | 15 | 1521690 | 101446 | 0 | 1736755.52 | 215065.52