## RABillBrowse_projwise6386512818
Project RA Bill
Magnolia Signature
Bill Date From 01/09/2024 To 20/10/2024
Page 1 of 1
Total Records: 20 Records 1 To 20
Project | WO NO | RABill Sr.No | RA Bill Date | Cont Bill No | Contractor | Executed_By | Voucher_No | TASK | Labour_Name | Qty | Unit | Rate | PS % | Retention_Amt | Total_RetRelease | WC_Amount | Tax_Scheme_Name | Tax Amount | Amount with Tax | Total Amount | Status | Credits | Debits | TDS_Amt | Due Date
Magnolia Signature | 29 | 1993 | 03 Oct 2024 | SKE/016/24-25 | S.K.ENTERPRISE (LABOUR CONT) | S.K.ENTERPRISE (LABOUR CONT) | JV - 1166 | SITE DEVELOPMENT WORK JHAMA ROAD | Construction of Road by jhama work all complete | 259.56 | Sq.M. | 510 | 100 | 0 | 0 | 132375.6 | I/P C+SGST 18% | 23827.6 | 156203.2 | 156203.2 | Approved | 0 | 0 | 1324 | 03 Dec 2024
Magnolia Signature | 30 | 1988 | 07 Oct 2024 | SLE/MSN/16/24-25 | SOLVE ENGINEERING PRIVATE LIMITED | SOLVE ENGINEERING PRIVATE LIMITED | JV - 1158 | BLOCK-3 Inside Brickwork | Inside Brickwork | 33543 | SQ.FT | 50 | 100 | 0 | 0 | 1677150 | I/P C+SGST 18% | 301887 | 1979037 | 1979037 | Approved | 0 | 0 | 118154 | 07 Dec 2024
Magnolia Signature | 30 | 1988 | 07 Oct 2024 | SLE/MSN/16/24-25 | SOLVE ENGINEERING PRIVATE LIMITED | SOLVE ENGINEERING PRIVATE LIMITED | JV - 1158 | ALL PLASTERING Inside Plaster | Inside plaster | 67096 | SQ.FT | 25 | 100 | 0 | 0 | 1677400 | I/P C+SGST 18% | 301932 | 1979332 | 1979332 | Approved | 0 | 0 | 118154 | 07 Dec 2024
Magnolia Signature | 30 | 1988 | 07 Oct 2024 | SLE/MSN/16/24-25 | SOLVE ENGINEERING PRIVATE LIMITED | SOLVE ENGINEERING PRIVATE LIMITED | JV - 1158 | BL-6 4th SLAB & BEAM RCC | RCC for Column/Slab/Beam | 4190 | SQ.FT | 150 | 100 | 0 | 0 | 628500 | I/P C+SGST 18% | 113130 | 741630 | 741630 | Approved | 0 | 0 | 118154 | 07 Dec 2024
Magnolia Signature | 30 | 1988 | 07 Oct 2024 | SLE/MSN/16/24-25 | SOLVE ENGINEERING PRIVATE LIMITED | SOLVE ENGINEERING PRIVATE LIMITED | JV - 1158 | BL-6 5th/ROOF SLAB & BEAM RCC | RCC for Column/Slab/Beam | 4290 | SQ.FT | 150 | 100 | 0 | 0 | 643500 | I/P C+SGST 18% | 115830 | 759330 | 759330 | Approved | 0 | 0 | 118154 | 07 Dec 2024
Magnolia Signature | 30 | 1988 | 07 Oct 2024 | SLE/MSN/16/24-25 | SOLVE ENGINEERING PRIVATE LIMITED | SOLVE ENGINEERING PRIVATE LIMITED | JV - 1158 | BLOCK-5 2nd FLOOR SLAB | RCC for Column/Slab/Beam | 8541 | SQ.FT | 150 | 100 | 0 | 0 | 1281150 | I/P C+SGST 18% | 230607 | 1511757 | 1511757 | Approved | 0 | 0 | 118154 | 07 Dec 2024
Magnolia Signature | 28 | 1987 | 01 Oct 2024 | 18 | M J H CONSTRUCTION (MUSARAF HOSSAIN) | M J H CONSTRUCTION (MUSARAF HOSSAIN) | JV - 1149 | SITE DEVELOPMENT WORK Miscellaneous Civil Work | LABOUR CHARGES FOR HELPER | 39 | Nos. | 550 | 100 | 0 | 0 | 21450 | I/P C+SGST URD | 0 | 21450 | 21450 | Approved | 0 | 0 | 292 | 01 Dec 2024
Magnolia Signature | 28 | 1987 | 01 Oct 2024 | 18 | M J H CONSTRUCTION (MUSARAF HOSSAIN) | M J H CONSTRUCTION (MUSARAF HOSSAIN) | JV - 1149 | SITE DEVELOPMENT WORK Miscellaneous Civil Work | LABOUR CHARGES FOR MASON | 6 | Nos. | 650 | 100 | 0 | 0 | 3900 | I/P C+SGST URD | 0 | 3900 | 3900 | Approved | 0 | 0 | 292 | 01 Dec 2024
Magnolia Signature | 28 | 1987 | 01 Oct 2024 | 18 | M J H CONSTRUCTION (MUSARAF HOSSAIN) | M J H CONSTRUCTION (MUSARAF HOSSAIN) | JV - 1149 | SITE DEVELOPMENT WORK Miscellaneous Civil Work | SUPERVISION CHARGES (15%) | 1 | Lumpsum | 3802.5 | 100 | 0 | 0 | 3802.5 | I/P C+SGST URD | 0 | 3802.5 | 3802.5 | Approved | 0 | 0 | 292 | 01 Dec 2024
Magnolia Signature | 27 | 1968 | 03 Oct 2024 | 27 | M J H CONSTRUCTION (MUSARAF HOSSAIN) | M J H CONSTRUCTION (MUSARAF HOSSAIN) | JV - 1110 | SITE DEVELOPMENT WORK SOLING | SOLING LABOUR | 27838.9 | SFT | 8 | 100 | 0 | 0 | 222711.2 | I/P C+SGST URD | 0 | 222711.2 | 222711.2 | Approved | 0 | 0 | 2227 | 03 Dec 2024
Magnolia Signature | 26 | 1962 | 24 Sep 2024 | SKE/015/2024-25 | S.K.ENTERPRISE (LABOUR CONT) | S.K.ENTERPRISE (LABOUR CONT) | JV - 1075 | SITE DEVELOPMENT WORK JHAMA ROAD | Construction of Road by jhama work all complete | 470.24 | Sq.M. | 510.38 | 100 | 0 | 0 | 240001.09 | I/P C+SGST 18% | 43200.2 | 283201.29 | 283201.29 | Approved | 0 | 0 | 2400 | 24 Nov 2024
Magnolia Signature | 25 | 1915 | 02 Sep 2024 | 10 | M J H CONSTRUCTION (MUSARAF HOSSAIN) | M J H CONSTRUCTION (MUSARAF HOSSAIN) | JV - 937 | SITE DEVELOPMENT WORK Miscellaneous Civil Work | LABOUR CHARGES FOR HELPER | 138 | Nos. | 550 | 100 | 0 | 0 | 75900 | I/P C+SGST URD | 0 | 75900 | 75900 | Approved | 0 | 0 | 1007 | 02 Nov 2024
Magnolia Signature | 25 | 1915 | 02 Sep 2024 | 10 | M J H CONSTRUCTION (MUSARAF HOSSAIN) | M J H CONSTRUCTION (MUSARAF HOSSAIN) | JV - 937 | SITE DEVELOPMENT WORK Miscellaneous Civil Work | LABOUR CHARGES FOR MASON | 18 | Nos. | 650 | 100 | 0 | 0 | 11700 | I/P C+SGST URD | 0 | 11700 | 11700 | Approved | 0 | 0 | 1007 | 02 Nov 2024
Magnolia Signature | 25 | 1915 | 02 Sep 2024 | 10 | M J H CONSTRUCTION (MUSARAF HOSSAIN) | M J H CONSTRUCTION (MUSARAF HOSSAIN) | JV - 937 | SITE DEVELOPMENT WORK Miscellaneous Civil Work | SUPERVISION CHARGES (15%) | 1 | Lumpsum | 13140 | 100 | 0 | 0 | 13140 | I/P C+SGST URD | 0 | 13140 | 13140 | Approved | 0 | 0 | 1007 | 02 Nov 2024
Magnolia Signature | 24 | 1908 | 02 Sep 2024 | SLE/MSN/15/24-25 | SOLVE ENGINEERING PRIVATE LIMITED | SOLVE ENGINEERING PRIVATE LIMITED | JV - 907 | BLOCK-4 Inside Brickwork | Inside Brickwork | 33545 | SQ.FT | 50 | 100 | 0 | 0 | 1677250 | I/P C+SGST 18% | 301905 | 1979155 | 1979155 | Approved | 0 | 0 | 150834 | 02 Nov 2024
Magnolia Signature | 24 | 1908 | 02 Sep 2024 | SLE/MSN/15/24-25 | SOLVE ENGINEERING PRIVATE LIMITED | SOLVE ENGINEERING PRIVATE LIMITED | JV - 907 | BLOCK-2 ALL FLOOR BRICK WORK Inside Brickwork | Inside Brickwork | 33548 | SQ.FT | 50 | 100 | 0 | 0 | 1677400 | I/P C+SGST 18% | 301932 | 1979332 | 1979332 | Approved | 0 | 0 | 150834 | 02 Nov 2024
Magnolia Signature | 24 | 1908 | 02 Sep 2024 | SLE/MSN/15/24-25 | SOLVE ENGINEERING PRIVATE LIMITED | SOLVE ENGINEERING PRIVATE LIMITED | JV - 907 | BLOCK-1 Inside Brickwork | Inside Brickwork | 33548 | SQ.FT | 50 | 100 | 0 | 0 | 1677400 | I/P C+SGST 18% | 301932 | 1979332 | 1979332 | Approved | 0 | 0 | 150834 | 02 Nov 2024
Magnolia Signature | 24 | 1908 | 02 Sep 2024 | SLE/MSN/15/24-25 | SOLVE ENGINEERING PRIVATE LIMITED | SOLVE ENGINEERING PRIVATE LIMITED | JV - 907 | BLOCK-5 4th FLOOR rcc for column/slab/beam | RCC for Column/Slab/Beam | 8322 | SQ.FT | 150 | 100 | 0 | 0 | 1248300 | I/P C+SGST 18% | 224694 | 1472994 | 1472994 | Approved | 0 | 0 | 150834 | 02 Nov 2024
Magnolia Signature | 24 | 1908 | 02 Sep 2024 | SLE/MSN/15/24-25 | SOLVE ENGINEERING PRIVATE LIMITED | SOLVE ENGINEERING PRIVATE LIMITED | JV - 907 | BL-6 2nd SLAB & BEAM RCC | RCC for Column/Slab/Beam | 4190 | SQ.FT | 150 | 100 | 0 | 0 | 628500 | I/P C+SGST 18% | 113130 | 741630 | 741630 | Approved | 0 | 0 | 150834 | 02 Nov 2024
Magnolia Signature | 24 | 1908 | 02 Sep 2024 | SLE/MSN/15/24-25 | SOLVE ENGINEERING PRIVATE LIMITED | SOLVE ENGINEERING PRIVATE LIMITED | JV - 907 | BL-6 3rd SLAB & BEAM RCC | RCC for Column/Slab/Beam | 4219 | SQ.FT | 150 | 100 | 0 | 0 | 632850 | I/P C+SGST 18% | 113913 | 746763 | 746763 | Approved | 0 | 0 | 150834 | 02 Nov 2024